## Mobile Banking_IB
S.No | Integration ID | Use Case | Interface Description | IIB Interface | Source | Target | Integration Pattern | IIB/ETL | Project | LLDs | Section/LLD | Tech Mapping | Tech Mapping / Tab | Current Status | UAT Status | UAT Comments
| Integration ID | Use Case | Interface Description | IIB Interface | Source | Target | Integration Pattern | IIB/ETL | Project | LLDs | Section/LLD | Tech Mapping | Tech Mapping / Tab | Current Status | UAT Status | UAT Comments | IBM Comments
1 | INT_BNK_MB_001 | Account Balance Enquiry | Balance summary for a particular account number | CASA_RD_MiniStatementCBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_q0cNQPNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.6 | Attached in LLD | CASARDMini | In Production | In Production
2 | INT_BNK_MB_002 | Account Mini Statement | Mini statement for a account number | CASA_RD_MiniStatementCBS_MF.msgflow | Mobile Banking | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.6 | Attached in LLD | CASARDMini | Duplicate | Duplicate | INT_BNK_MB_001 | Agree
3 | INT_BNK_MB_003 | Loan Account information | Loan account statements with customers loan details. List of all Loans and its details | LoanBalanceInq_CBS_MF.msgflow LoanEMISchedule_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rHsgcPNcEeagF9-F41OIKA https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rH570PNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.18,2.39 | Attached in LLD | LoanBLInq LoanEMISch | In Production | In Production | Loan linked to customer are visible in 360 degree page | ?
4 | INT_BNK_MB_004 | Term Deposit Account | Term deposit account statements. List of all TD's for a customer based on customer ID | TDBalanceInq_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_qwZawPNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.10 | Attached in LLD | TdBlncInq | In Production | In Production | No Depoist statement is available. Deposit details will be displayed | This summery of TD acocunt
5 | INT_BNK_MB_005 | RD account information | RD account statements. List of all RD's for a customer based on customer ID | CASA_RD_BalanceInq_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_q0U4gPNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.4 | Attached in LLD | CASARD_blnc_inq | In Production | In Production | No Depoist statement is available.Deposit details will be displayed | This summery of RD acocunt
9 | INT_BNK_MB_009 | Fund transfer - to Mobile no. - For IMPS (P2P) | Fund transfer - to Mobile no. - For IMPS | FundXferP2P_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_q6ZrUPNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.16 | Attached in LLD | FndTnfrP2P | In Production | UAT Pending due to external dependency | UAT will be complted once end to end testing is completed post ROC
10 | INT_BNK_MB_010 | Fund transfer - to Account no. - For IMPS (P2A) | Fund transfer - to Account no. - For IMPS | FundXferP2P_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_q6ZrUPNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.16 | Attached in LLD | FndTnfrP2P | In Production | UAT Pending due to external dependency | UAT will be complted once end to end testing is completed post ROC
11 | INT_BNK_MB_011 | IMPS Merchant Payment | IMPS Merchant Payment |  | Mobile Banking | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc |  |  |  | Descoped | Descoped | Was descoped at the requirement stage and never came till UAT | Agree.
12 | INT_BNK_MB_012 | Generate / Retrieve / Cancel MMID | Generate / Retrieve / Cancel MMID | GenerateMMID_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rLFLoPNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.25 | Attached in LLD | GnrtMMID | In Production | In Production | Retrive and Cancel MMID options are available. | Only Retrieve/Generate MMID available , Updated interface description
18 | INT_BNK_MB_018 | Fund transfer - to Account no. - For NEFT | Fund transfer - to Account no. - For NEFT | FundXferNEFT_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_q6OsMPNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.14 | Attached in LLD | FundTrnsfrNFT | In Production | UAT Pending due to external dependency | UAT will be complted once end to end testing is completed post ROC
19 | INT_BNK_MB_019 | Request for Stop Payment of Cheque | Request stop cheque payment | ChequeStopReq_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rLA6MPNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.24 | Attached in LLD | ChqStopReq | In Production | In Production
20 | INT_BNK_MB_020 | Cheque Status Enquiry | Request for status of cheque | ChequeStatusInq_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rK8owPNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.23 | Attached in LLD | ChqStsInqCBS | In Production | In Production
21 | INT_BNK_MB_021 | Request for Cheque book | Request for new cheque book | ChequeBookReq_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rK4XUPNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.22 | Attached in LLD | ChqBookReq | In Production | In Production
22 | INT_BNK_MB_022 | View status of fund transfer | Status of funds transfer - all funds transfer initiated and active | FundXferHistory_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_q6FiQPNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.37 | Attached in LLD | FundXferHistory_CBS | In Production | In Production | FT history searcg by payee name is pending in Internet Banking - 29782 | API only supports Customer ID/ Account only. 27Dec: Payee name filtering doesn’t happen in IIB service. IIB Service is working as expected. The payee name filtering to be looked at as part of IB project
23 | INT_BNK_MB_023 | Creation of Recurring Deposit | Create new RD account | OpenRDTDAccount_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_jv0XoNBNEeevSbFzOMe4EA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.7 | Attached in LLD | OpenRDTDAccount | In Production | In Production
24 | INT_BNK_MB_024 | Creation of Fixed Deposit | Create new FD account | OpenRDTDAccount_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_jv0XoNBNEeevSbFzOMe4EA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.7 | Attached in LLD | OpenRDTDAccount | In Production | In Production
27 | INT_BNK_MB_027 | Fetch EMI Due dates | Get the list of due dates for all EMI to be paid | LoanEMISchedule_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rH570PNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.39 | Attached in LLD | LoanEMISchedule | In Production | In Production |  | It's available.
28 | INT_BNK_MB_028 | Request loan re-schedule | Reschedule the EMI payment date for a active loan (Taken care in SFDC service request) |  | Mobile Banking | SFDC | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc |  |  |  | Descoped | Descoped | Was descoped at the requirement stage and never came till UAT | This requiremnet was dropped for Loan reschedule
29 | INT_BNK_MB_029 | Applying for a loan | Apply for new loan from Mobile app | LMS_CreateLead_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_iDJlANBOEeevSbFzOMe4EA | SFDC | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.40 | Attached in LLD | LeadCrt_LMS | In Production | In Production
43 | INT_BNK_MB_043 | Request new debit card | Request for new debit card (Taken card as part of SFDC service request) | LMS_CreateLead_MF.msgflow | Mobile Banking | SFDC | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc |  |  |  | Duplicate | Duplicate | INT_BNK_MB_043 | Agree
44 | INT_BNK_MB_044 | Block debit card | Block debit card | FIS_Gateway_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_3MoYguw2EeaKccH3UdS-jQ&itemType=com.ibm.team.filesystem.FileItem&itemId=_AZAeQNBREeevSbFzOMe4EA | FIS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-FIS Services-LLD v0.3.docx | 4.19 | Attached in LLD | NA | In Production | In Production
45 | INT_BNK_MB_045 | Get last transaction detail | Get the details of last transaction | Same as mini statement of CASA | Mobile Banking | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc |  |  |  | Duplicate | Duplicate | INT_BNK_MB_002 | agree
46 | INT_BNK_MB_046 | Service request status inquiry | Inquire the status of service requests made (Covered in INT_BNK_MB_121) | RetrieveCust360Info_SFDC_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_rc74sEdaEea8rpH8mea1fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_hQvJQdBREeevSbFzOMe4EA | SFDC | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-Liabilities Services-LLD v0.3.docx | 2.3 | Attached in LLD | RetrieveCust360Info_SFDC | In Production | In Production
49 | INT_BNK_MB_049 | Retrieve all assets and liabilites of customer | Display in dashboard all assets and liabilities of a custoemr | Customer360Inq_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_q0mlUPNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.5 | Attached in LLD | Customer360Inq | In Production | In Production | Customer 360 Degree View
50 | INT_BNK_MB_050 | Configure / Update Email ID | Update or configure the Email ID of the customer | UpdateEmailIDCBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rLnXIPNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.28 | Attached in LLD | UpdateEmailIDCBS | In Production | In Production
54 | INT_BNK_MB_054 | Fund transfer history | Get the history of funds transfer | FundXferHistory_CBS_MF.msgflow | Mobile Banking | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc |  |  |  | Duplicate | Duplicate | INT_BNK_MB_022
54 | INT_BNK_MB_055 | Bill Pay - Add | Add a new Bill pay | RegisterPay_AddBiller_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_q3ikkPNcEeagF9-F41OIKA | BillDesk | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-BilldeskServices-LLD_v0.2.docx | 2.3 | Attached in LLD | AddBiller | In Production | In Production | Bill pay module required to be re configured. As discussed in the 27 Dec meeing, marking as Yes as this was tested in UAT. | Service is build and deployed
56 | INT_BNK_MB_056 | Bill Pay - Delete | Delete a Bill pay | RegisterPay_DeleteBiller_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_q4gN4PNcEeagF9-F41OIKA | BillDesk | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-BilldeskServices-LLD_v0.2.docx | 2.4 | Attached in LLD | RegisterPay_DeleteBiller | In Production | In Production | Bill pay module required to be re configured. As discussed in the 27 Dec meeing, marking as Yes as this was tested in UAT. | Service is build and deployed
57 | INT_BNK_MB_057 | Bill Pay - Schedule | Schedule a Bill Pay | RegisterPay_SetAutoPay_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rDhLEPNcEeagF9-F41OIKA | BillDesk | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-BilldeskServices-LLD_v0.2.docx | 2.9 | Attached in LLD | AutoPayBill | In Production | UAT Pending due to external dependency | Bill pay module required to be re configured. Scheduled Bill pay was not tested in uAT | This service is available but has not tested yet due to dependency on JFS , setup is not agreed with billdesk
58 | INT_BNK_MB_058 | Bill Pay - History | Get bill pay history | RegisterPay_ScheduledBills_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rDgkAfNcEeagF9-F41OIKA | BillDesk | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-BilldeskServices-LLD_v0.2.docx | 2.11 | Attached in LLD | ViewSchdBill | In Production | In Production | Bill pay module required to be re configured.As discussed in the 27 Dec meeing, marking as Yes as this was tested in UAT. | Service is build and deployed
59 | INT_BNK_MB_059 | Bill Pay - Disable Auto Pay | Disable auto bill pay | RegisterPay_StopScheduleTran_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rDmqoPNcEeagF9-F41OIKA | BillDesk | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-BilldeskServices-LLD_v0.2.docx | 2.10 | Attached in LLD | StopSchdlTxn | In Production | UAT Pending due to external dependency | Bill pay module required to be re configured. Auto Bill pay was not tested in uAT | This service is available but has not tested yet due to dependency on JFS , setup is not agreed with billdesk
60 | INT_BNK_MB_060 | Bill Pay - Presented Bill | Get presented bill pay | RegisterPay_ViewBills_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_q4wskPNcEeagF9-F41OIKA | BillDesk | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-BilldeskServices-LLD_v0.2.docx | 2.6 | Attached in LLD | ViewBIll | In Production | In Production | Bill pay module required to be re configured. This functionality is tested in UAT using data from back end | Service is build and deployed
62 | INT_BNK_MB_062 | Loan statement | View the account statement for a loan | LoanMinistatement_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rIHXMPNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.19 | Attached in LLD | LoanMiniStmt | In Production | In Production
63 | INT_BNK_MB_063 | Email Statement | Email the account statement | CASA_RD_MiniStatementCBS_MF.msgflow | Mobile Banking | Email | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc |  |  |  | Duplicate | Duplicate | INT_BNK_MB_002
64 | INT_BNK_MB_064 | Generate OTP | Generate OTP for transctions | GenerateSMS_MBank_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_q5cCAPNcEeagF9-F41OIKA | RouteSMS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.38 | Attached in LLD | GnrtSMSCBS | In Production | In Production
65 | INT_BNK_MB_065 | Mobile / DTH / Data Card Recharge | Recharge Mobile / DTH / DC from Mobile App | Recharge_PaymentsDetails_MF.msgflow Recharge_ValidateDetails_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_5SWaENBPEeevSbFzOMe4EA https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_5Sdu0NBPEeevSbFzOMe4EA | BillDesk | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-BilldeskServices-LLD_v0.2.docx | 2.12 | Attached in LLD | PayDtlsBillDesk ValidtDtlspaybill | In Production | In Production | Bill pay module required to be re configured. As discussed in the 27 Dec meeing, marking as Yes as this was tested in UAT. | Service is build and deployed
67 | INT_BNK_MB_067 | Details of Transantion | To display the details of a particular transaction. | FundXferHistory_CBS_MF.msgflow | Mobile Banking | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc |  |  |  | Duplicate | Duplicate | INT_BNK_MB_054
68 | INT_BNK_MB_068 | Loan Payment | Make EMI Payment | LoanPaymentCBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rIWAsPNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.20 | Attached in LLD | LoanPymtCBS | In Production | In Production
73 | INT_BNK_MB_073 | Fund Transfer - Own Account | Fund transfer to own account | FundXferIntra_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_jtZVwNBNEeevSbFzOMe4EA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.13 | Attached in LLD | FundXferIntra_CBS_MF | In Production | In Production
74 | INT_BNK_MB_074 | Fund Transfer - Jana Bank | Fund transfer to other account within Jana bank | FundXferIntra_CBS_MF.msgflow | Mobile Banking | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc |  |  |  | Duplicate | Duplicate | INT_BNK_MB_073
76 | INT_BNK_MB_076 | Get New Product | Details about all products of the bank. (Taken card as part of SFDC service request) | LMS_CreateLead_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_iDJlANBOEeevSbFzOMe4EA | SFDC | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.40 | Attached in LLD | LeadCrt_LMS | In Production | In Production | New offering request from Mobile Banking
79 | INT_BNK_MB_079 | TD Statement | TD statement |  | Mobile Banking | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc |  |  |  | Descoped | Descoped | Was descoped at the requirement stage and never came till UAT | This summery of TD acocunt 27Dec:Duplicate of row 6
80 | INT_BNK_MB_080 | RD Statement | RD statement |  | Mobile Banking | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc |  |  |  | Descoped | Descoped | Was descoped at the requirement stage and never came till UAT | This summery of RD acocunt 27Dec:Duplicate of row 7
84 | INT_BNK_MB_084 | Fund Transfer - RTGS | Fund transfer using RTGS | FundXferRTGS_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_q6fx8PNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.14 | Attached in LLD | FndTrnfrNTGS | In Production | UAT Pending due to external dependency | UAT will be complted once end to end testing is completed post ROC | Service is build and deployed
85 | INT_BNK_MB_085 | Close RD | Close Recurring deposit | AccountClosureRD_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_quFtoPNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.11 | Attached in LLD | ActClousrRD | In Production | In Production
86 | INT_BNK_MB_086 | Close FD | Close Fixed Deposit | AccountClosureTD_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_quRT0PNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.12 | Attached in LLD | ActClousrTD | In Production | In Production
87 | INT_BNK_MB_087 | Card Registration - First Log in | Card Registration - First Log in | CardActivationFIS_MF.msgflow CheckPinFIS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_jw5VsNBNEeevSbFzOMe4EA https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_jw9AENBNEeevSbFzOMe4EA | FIS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-FIS Services-LLD v0.3.docx | 4.13 4.14 | Attached in LLD | CardActivationFIS_MF CheckPinFIS_MF | In Production | In Production
92 | INT_BNK_MB_092 | Usage of Mobile App Prior to A/C Opening Apply for CASA | Apply for new CASA (Taken card as part of SFDC service request) | LMS_CreateLead_MF.msgflow | Mobile Banking | SFDC | Sync Req/Reply | iIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc |  |  |  | Duplicate | Duplicate | INT_BNK_MB_076
98 | INT_BNK_MB_098 | New/additional loan | Apply for a New or additional loan (Taken card as part of SFDC service request) | LMS_CreateLead_MF.msgflow | Mobile Banking | SFDC | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc |  |  |  | Duplicate | Duplicate | INT_BNK_MB_076
99 | INT_BNK_MB_099 | Utilities Payment - Bill Aggregator Billdesk |  | RegisterPay_PayBills_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_q4ltcPNcEeagF9-F41OIKA | BillDesk | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-BilldeskServices-LLD_v0.2.docx | 2.7 | Attached in LLD | PayBills | In Production | In Production | Bill pay module required to be re configured As discussed in the 27 Dec meeing, marking as Yes as this was tested in UAT by inserting the bill details in Back end | Service is build and deployed
100 | INT_BNK_MB_100 | Billpay - Instant Bill Pay | Insta Bill pay | InstaPay_BillFetch_MF.msgflow RegisterPay_PayBills_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_q3N0cPNcEeagF9-F41OIKA | BillDesk | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-BilldeskServices-LLD_v0.2.docx | 2.5 2.7 | Attached in LLD | fetchBill PayBills | In Production | In Production | Bill pay module required to be re configured. As discussed in the 27 Dec meeing, marking as Yes as this was tested in UAT. | Service is build and deployed
102 | INT_BNK_MB_102 | Funds Transfer - within Jana Bank | One Time Funds Transfer - Jana Bank Customer | FundXferIntra_CBS_MF.msgflow | Mobile Banking | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc |  |  |  | Duplicate | Duplicate | There is no interface defined for one time transfer between jana bank customers. 27Dec: This is duplicate of row 73 | Agree
103 | INT_BNK_MB_103 | Funds Transfer - One Time Transfer - Other Bank Customer | One Time Funds Transfer - Other Bank Customer | FundXferRTGS_CBS_MF.msgflow | Mobile Banking | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc |  |  |  | Duplicate | Duplicate | There is no interface defined for one time intra bank transfer. 27Dec: Duplicate of Row 20 & 86 | Agree
104 | INT_BNK_MB_104 | Funds Transfer - One Time Transfer - Jana Pre-paid card | One Time Funds Transfer - Jana Pre-paid card | FundXferIntra_CBS_MF.msgflow FIS_Gateway_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_jtZVwNBNEeevSbFzOMe4EA | FIS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.13 | Attached in LLD | FundXferIntra_CBS_MF | In Production | In Production | Pre paid card loading using CASA is available | Load money into card is available
108 | INT_BNK_MB_108 | Funds Transfer - Jana-prepaid Card | Funds Transfer - Jana-prepaid Card | Requirement Dropped by JFS | Mobile Banking | FIS | Sync Req/Reply | IIB | JFS Bank Transition | NA |  |  |  | Deffered | In Production | Transfer to own pre-paid card only
110 | INT_BNK_MB_110 | My Account with balance meter - Deposit A/C Bal - TD Calculator | To calculate the maturity ammount and interest rate before TD account opening | TDMaturityCalc_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_jwMyIdBNEeevSbFzOMe4EA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.9 | Attached in LLD | TdMturCalc | In Production | In Production | While booking Deposit, application will display the maturity amount | updated description of service
111 | INT_BNK_MB_111 | My Account with balance meter - Deposit A/C Bal - TDS Enquiry | TDS inquiry for Deposit |  | Mobile Banking | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc |  |  |  | Descoped | Descoped | Was descoped at the requirement stage and never came till UAT | Agree
112 | INT_BNK_MB_112 | My Account with balance meter - Wallet A/C Balance - Last 10 transactions | Last 10 transactions for Wallet A/C. | BalanceInq_mFino_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rGZf8PNcEeagF9-F41OIKA | mFino | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.36 | Attached in LLD | BlncInqmFino | In Production | In Production |  | Its available in MB
119 | INT_BNK_MB_119 | Validate within bank account number | Fetch account Name based on Account number. | CASA_RD_BalanceInq_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_q0U4gPNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.4 | Attached in LLD | CASARD_blnc_inq | In Production | In Production
121 | INT_BNK_MB_121 | Customer 360 view | Get the customer account related information from SFDC system. Based on FIS returned Account #, SFDC needs to return the 360 degree view of the customer and their customer reference number in each system. And provides list of SR raised and details of SR | RetrieveCust360Info_SFDC_MF.msgflow?? | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_rc74sEdaEea8rpH8mea1fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_hQvJQdBREeevSbFzOMe4EA | SFDC | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | Liabilities | Attached in LLD | Refer Liabilities | In Production | In Production
122 | INT_BNK_MB_122 | Create generic service in SFDC | TD/RD Closure, stop cheque, Block card, Card PIN change, Cheque Book, loan re-schedule, New Products (Existing/New customer), New card, Update email, | GenerateMMID_CBS_MF.msgflow mbank_LogSR_SFDC_MF.msgflow UpdateEmailIDCBS_MF.msgflow UpdateProfile_mbank_MF.msgflow UpdateProfileGateway_MF.msgflow UpdateProfileStatusSFDC_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rLnXIPNcEeagF9-F41OIKA https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rLrBgPNcEeagF9-F41OIKA https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rNbVAPNcEeagF9-F41OIKA https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rAXwcPNcEeagF9-F41OIKA | SFDC | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.25 2.21 2.28 2.29 2.31 2.41 | Attached in LLD | GnrtMMID mbank_LogSR_SFDC UpdateEmailIDCBS_MF UpdateProfile_mBank UpdateProfileGateway UpdateProfileStatusSFDC | In Production | In Production | Case id can be queried using status inquiry option. When RD/TD is closed then Service request is created | SR is available to log the service request for TD/RD closure & new card into SFDC.
123 | INT_BNK_MB_123 | Configure / Update Email ID | Update or configure the Email ID of the customer | UpdateProfileFIS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_jxnHYNBNEeevSbFzOMe4EA | FIS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-FIS Services-LLD v0.3.docx | 4.18 | Attached in LLD | UpdateProfileFIS_MF | In Production | In Production
124 | INT_BNK_MB_124 | Configure / Update Email ID | Update or configure the Email ID of the customer | UpdateEmailID_mFino_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rGkfEPNcEeagF9-F41OIKA | mFino | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.30 | Attached in LLD | UpdateEmailID_mFino | In Production | In Production
125 | INT_BNK_MB_125 | RD Calculator | RD Maturity calculator | RDMaturityCalc_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_jwGEcNBNEeevSbFzOMe4EA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.9 | Attached in LLD | RDMaturityCalc_CBS | In Production | In Production | This not actual calculator but during creation maturity amount will be shown | Its available in MB
126 | INT_BNK_MB_126 | Service Charge Inquiry | Calulate service charge amount for fund transfer | ServiceChargeInq_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_q8Kl4PNcEeagF9-F41OIKA | CBS | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.17 | Attached in LLD | ServiceChargeInq_CBS | In Production | In Production | Service charge inquiry is not available as an option but service charge amount is computed during the fund transfer will be displayed. | It's available MB
127 | INT_BNK_MB_127 | Wallet 360 view | Retrive all wallet details for a URN | BalanceInq_mFino_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rGZf8PNcEeagF9-F41OIKA | mFino | Sync Req/Reply | IIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.36 | Attached in LLD | BlncInqmFino | In Production | In Production | Only wallet balance and txns | Available as wallet 360 - Txns are available
128 | INT_BNK_MB_128 | Card 360 view | Card 360 view | CustomerViewFIS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_jxAqcNBNEeevSbFzOMe4EA | FIS | Sync Req/Reply | iIB | JFS Bank Transition | JFS-IIB-FIS Services-LLD v0.3.docx | 4.15 | Attached in LLD | CustomerViewFIS_MF | In Production | In Production | Pre-paidcard details | Updated the interface name
129 | INT_BNK_MB_129 | Card statement | Card mini statement | MiniStatement_MF | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_3MoYguw2EeaKccH3UdS-jQ&itemType=com.ibm.team.filesystem.FileItem&itemId=_WBGwIPN7EeaqsbSDi1YdmQ | FIS | Sync Req/Reply | iIB | JFS Bank Transition | JFS-IIB-FIS Services-LLD v0.3.docx | 4.7 | Attached in LLD | available in FOS LLD | In Production | In Production | Pre-paidcard details | Agree
130 | INT_BNK_MB_130 | Set/Modify/Delete Standing Instruction | Set/Modify/Delete Standing Instruction | SI_CASA_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_rLieoPNcEeagF9-F41OIKA | CBS | Sync Req/Reply | iIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.27 | Attached in LLD | SI_CASA_MF | In Production | In Production
131 | INT_BNK_MB_131 | Standing Instruction Inquiry | Standing Instruction Inquiry | SI_CASAInquiry_CBS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_q_094PNcEeagF9-F41OIKA | CBS | Sync Req/Reply | iIB | JFS Bank Transition | JFS-IIB-MobileBankingAndContactCentreServices-LLD 0.5.doc | 2.27 | Attached in LLD | SI_CASAInquiry_CBS | In Production | In Production
132 | INT_BNK_MB_131 | Card Number & Card PIN Verification | Debit Card Number and PIN Validation (Once verified, the API will respond back with the customer id, mail id & Mobile Number) | CheckPinFIS_MF.msgflow | https://jfsuatapptrf1.janalakshmi.com:9444/ccm/web/projects/JFS_IIB#action=com.ibm.team.scm.browseElement&workspaceItemId=_llmfENvdEeaFZJ3xvtM0fw&componentItemId=_Xx1CcpnMEeaxM7J7pfx8Fg&itemType=com.ibm.team.filesystem.FileItem&itemId=_jw9AENBNEeevSbFzOMe4EA | FIS | Sync Req/Reply | iIB | JFS Bank Transition | JFS-IIB-FIS Services-LLD v0.3.docx | 4.14 | Attached in LLD | CheckPinFIS_MF | In Production | In Production
Note on C73: ADMINIBM: Mode of communication not confirmed as PCI compliance needs to be fullfilled.